## TruthLens Progress Log
Date | Learning Focus | Work Completed | Tools/Concepts
2026-02-10 | Project idea & fake news detection basics | Defined TruthLens AI goal and project scope | NLP, Fake News Detection
2026-02-11 | Python project structuring | Created repo structure and folders | Python, Git
2026-02-12 | Dataset research | Identified ISOT, LIAR, FakeNewsNet datasets | Datasets, Research
2026-02-13 | Data loading methods | Implemented dataset loading utilities | Pandas, Data Processing
2026-02-14 | Dataset merging strategies | Built merge_datasets.py | Data Integration
2026-02-15 | Data cleaning techniques | Implemented clean_data.py | Text Cleaning
2026-02-16 | Data validation concepts | Built validate_data.py | Data Validation
2026-02-17 | EDA fundamentals | Implemented EDA module and plots | Matplotlib, Analysis
2026-02-18 | Feature engineering basics | Designed feature pipeline structure | Feature Engineering
2026-02-19 | Metadata features | Implemented metadata_features.py | Feature Extraction
2026-02-20 | Source credibility features | Created source_features.py | Domain Extraction
2026-02-21 | TF-IDF understanding | Implemented text_features.py | TF-IDF, NLP
2026-02-22 | Pipeline integration | Built feature_pipeline.py | Pipeline Architecture
2026-02-23 | Transformer models overview | Studied BERT/RoBERTa architecture | Transformers
2026-02-24 | HuggingFace basics | Learned tokenizers and Trainer API | HuggingFace
2026-02-25 | Model training setup | Created train_roberta.py training pipeline | PyTorch, HF Trainer
2026-02-26 | Training experiments | Ran initial model training runs | Model Training
2026-02-27 | Evaluation metrics | Implemented evaluation module | Accuracy, F1, Precision
2026-02-28 | Visualization | Built confusion matrix visualization | Visualization
2026-03-01 | Cross validation concepts | Implemented cross_validation.py | Model Validation
2026-03-02 | Hyperparameter tuning | Implemented Optuna tuning module | Optuna
2026-03-03 | Model saving/loading | Built model_utils.py | Serialization
2026-03-04 | Prediction pipeline | Implemented predict.py inference logic | Inference Pipeline
2026-03-05 | API fundamentals | Learned FastAPI basics | FastAPI
2026-03-06 | API implementation | Built api/app.py endpoints | REST API
2026-03-07 | Model serving flow | Integrated model inference with API | Model Serving
2026-03-08 | Configuration management | Built config.yaml + settings loader | Config Management
2026-03-09 | Logging and utilities | Added logging utilities and helpers | Logging
2026-03-10 | Testing basics | Created initial unit tests | Pytest
2026-03-11 | Dataset split strategies | Implemented train / validation / test split | Scikit-Learn
2026-03-12 | Data augmentation | Implemented dataset augmentation pipeline | Data Augmentation
2026-03-13 | Feature pipeline optimization | Added leakage-safe feature transformations | ML Pipeline Design
2026-03-14 | Feature caching | Implemented caching for feature extraction | Joblib
2026-03-15 | Model registry concept | Designed model registry for managing multiple models | Model Management
2026-03-16 | Multi-model architecture | Designed TruthLens multi-model system | Multi-Task Learning
2026-03-17 | Bias detection module | Implemented bias classification model | Political NLP
2026-03-18 | Propaganda detection module | Designed propaganda analysis workflow | Propaganda Detection
2026-03-19 | Narrative analysis | Implemented narrative framing detection | Narrative Analysis
2026-03-20 | Ideology classification | Built ideological orientation classifier | Political Ideology Detection
2026-03-21 | Emotion analysis | Implemented emotion classification module | Emotion NLP
2026-03-22 | Batch inference pipeline | Implemented large-scale article processing | Batch Processing
2026-03-23 | Prediction caching | Added inference caching for faster predictions | Caching Systems
2026-03-24 | Structured logging | Implemented structured inference logging | Monitoring
2026-03-25 | Visualization improvements | Added ROC curve and PR curve plots | Model Evaluation
2026-03-26 | Model evaluation analysis | Compared performance across tasks | ML Evaluation
2026-03-27 | Production pipeline prep | Prepared pipeline for deployment | ML Engineering
2026-03-28 | API improvement | Extended FastAPI endpoints and validation | FastAPI
2026-03-29 | Config refinement | Improved config.yaml and settings loader | Configuration Management
2026-03-30 | Logging enhancements | Expanded training and inference logging | Python Logging
2026-03-31 | Testing expansion | Added more PyTest unit tests | PyTest
2026-04-01 | Documentation update | Improved QuickStart and architecture docs | Technical Documentation
2026-04-02 | Inference optimization | Improved prediction pipeline speed | Inference Systems
2026-04-03 | Model artifact management | Organized model outputs and reports | Model Management
2026-04-04 | Evaluation reports | Generated structured evaluation result files | JSON Reports
2026-04-05 | System integration | Integrated multi-model outputs into pipeline | ML Systems
2026-04-06 | Final project review | Reviewed pipeline and prepared documentation for presentation | Project Documentation